## Requirement_Traceability_Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name | The Race to a New System
Project Type | Technical Organization
Project Start Date | 2017-02-15
Project End Date | 2017-05-02
Project Sponsor | Essential Systems
Primary Driver | Andrew Huff
Secondary Driver | Louis Ries
Division | Technology
Project Manager/Department | Robert Barker
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
001 | 007 | Payments can be made online. People need to order forms without having to travel to Louisville. | Process online payments | In Progress | User goes to the webpage and clicks to a document and enter their credit card information into the page. | A website will just need to embed the PayPal payment button. | PayPal linked button | PayPal
002 |  | Newsletter and easier communication to members | The business email will be used to send newsletters. | In Progress | Employee logs into new domain email to create and send emails or newsletters to members. | A newsletter signup and new domain will need to be created. | G- Suite | G- Suite
003 |  | A way to backup data will be needed. | Microsoft Azure will backup data. | In Progress | Database for the company and storage unit for important documents that are being stored in filing cabinets right now. | A Microsoft Azure account and setup will be required. | Microsoft Azure database and storage linked to website and domain email. | Microsoft Azure
004 | 003 | A recovery method is needed. | Microsoft Azure will hold data to be recovered. | In Progress | The data from the backups will just be opened to recovery files. | A Microsoft Azure account and setup will be required. | Microsoft Azure database and storage linked to website and domain email. | Microsoft Azure
005 |  | There needs to be a contact us page on the website. | Information is displayed for members to contact the company. | In Progress | The website will be programmed to show a contact us page. | The website will need to be formatted with a contact us page. | The website. | Website
006 | 014 | There needs to be an online login for members. | The members need to be able to use a unique I.D to login to the website. | In Progress | The website will have a login area that transfers data to a database. | The website will need to be connected to the database to pull the information when members log in. | Microsoft Azure database. | Microsoft Azure
007 | 001 | There needs to be an online donations page. | Members and other site visitors will be able to donate through the website. | In Progress | A user can go to the website and click the donate button to enter their credit card information into the page. | A PayPal donation button will be linked. | PayPal linked button | PayPal
008 |  | Members need to access the site via mobile devices. | Members will be able to view the website on their mobile device. | In Progress | The site will have a mobile compatibility. | The website will need to be formatted to a mobile compatibility. | The website. | Website
009 | 010 | Members need a way to print forms. | Members need to be able to print forms from the website. | In Progress | Printable forms or a pdf file will need to be available on a page. | The website will need to include printable forms. | The website. | Website
010 | 009 | Members need a way to scan documents. | Members need to be able to scan documents into their profile for situations like claims. | In Progress | There will need to be an option to upload documents into the website. | The website will need an uploads page. | The website. | Website
011 | 016 | Members need a way to upload photos. | Members need to be able to upload images from races or a member profile picture. | In Progress | There will need to be an option to upload photos into the website. | The website will need an uploads page. | The website. | Website
012 |  | The website needs links to social media. | Social media platforms need to be linked to the website for easier access. | In Progress | There will need to be social media links embedded. | The website will need a social media link embedded. | The website. | Website
013 | 012 | The website needs to push content from social media. | Social media feed need to be pushed to the website to keep content up to date. | In Progress | The links to social media need to show on the site. | The website will need a link to social media. | The website. | Website
014 |  | Members need an online sign up method. | Members need a way to sign up online. | In Progress | The website will need to take information entered and transfer it to a database. | The members will sing up and the information will be added to the database. | Microsoft Azure database. | Microsoft Azure
015 | 006 | Members need to view benefits. | Members need a way to view their current benefits. | In Progress | The website will need a page for benefits. | The website profiles will need a benefits page. | The website. | Website
016 |  | A photo gallery should be added to show members race photos and photos from other events. | Members need a way to view photos from races or other events. | In Progress | The website will need a place for photos to be gathered in a gallery. | The website will need photos to be enabled. | The website. | Website
017 | 006 | There needs to be a way to manage users. | The Kentucky Horsemen's Benevolent and Protective Association needs a way to manage current members and a way to manager online users. | In Progress | The database will need to see if the member has any active data for the season to decide if they are an active member. | The database will need to show which members are active. | Microsoft Azure database. | Microsoft Azure
018 | 022 | Upcoming events and important deadlines will need to be added in the calendar for members to see. | The Kentucky Horsemen's Benevolent and Protective Association need a way to keep content up to date and inform members of upcoming events. | In Progress | The website will need to be easily updated, and have an embedded link to transfer data from social media to the site. | The website will need the calendar to be easily updated. | The website. | Website
019 |  | There needs to be a way to poll members. | Important questions will be able to be asked if members can be polled. | In Progress | Employees can make polls on a third party website and post the link to the website. | An account with a third party polling system would be needed. | Third party website | Third party website.
020 | 005 | There needs to be an employee information page. | Employee information needs to be added to the page for members to contact them | In Progress | Employee information can be programmed into a separate page. | The website will need to be programmed. | The website. | Website
021 | 010 | There needs to be a way to process claims. | An online claims process needs to be added for member convenience. | In Progress | The website will need a way to process claims but also be HIPPA compliant. | The website will need to be programmed. | The website. | Website
022 | 013 | There needs to be a way to update news. | The members need to be informed of current issues that are too important to wait until a newsletter or calendar update. | In Progress | A way to update news quickly will need to be programmed into the website. | The website will need to be programmed. | The website. | Website
Note on A11: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B11: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C11: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on D11: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on E11: • Status: This column should be populated with the current status of the functional requirement.
Note on F11: • Architectural/Design Document: This column should be populated with a description of the architectural/design document linked to the functional requirement.
Note on G11: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on H11: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Note on I11: • Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Note on J11: • Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Note on K11: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on L11: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on M11: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.