## Requirement_Traceability_Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name | The Race to a New System
Project Type | Technical Organization
Project Start Date | 2017-02-15
Project End Date | 2017-05-02
Project Sponsor | Essential Systems
Primary Driver | Andrew Huff
Secondary Driver | Louis Ries
Division | Technology
Project Manager/Department | Krysta Albertson
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
001 | 1.1.1 | Payments can be made online. People need to donate online or order forms without having to travel to Louisville. | Process online payments | In Progress | User goes to the webpage and clicks donate or orders a document and enter their credit card informatiion into the page. | A website will just need to embed the PayPal payment button. | PayPal linked button | PayPal |  |  |  |  | Referenced in Use Case #13
002 | 2.2.2 | Newsletter and easier communication to members | Business Email | In Progress | Employee logs into new domain email to create and send emails or newsletters to members. | A newsletter signup and new domain will need to be created. | G- Suite | G- Suite |  |  |  |  | Referenced in Use Case #15
003 | 3.3.3 | Business continuity, storage, and disaster recovery | Microsoft Azure | In Progress | Database for the company and storage unit for important documents that are being stored in filing cabinets right now. | A Microsoft Azure account and setup will be required. | Microsoft Azure database and storage linked to website and domain email. | Microsoft Azure |  |  |  |  | Referenced in Use Case #22
004 | 4.4.4 | Form Submission | Ability for members to claim benefits / submit forms online | In Progress | User goes to webpage and clicks forms and then clicks submit from where users can upload their form. | A website will need a submission tool | file upload plugin | Website plugin |  |  |  |  | Referenced in Use Case #4
005 | 5.5.5 | Photo Gallery | View photos online | In Progress | User goes to the webpage and scrolls down to view photo gallery | A website will need to embed a photo gallery plugin | Photo gallery plugin | Website plugin |  |  |  |  | Referenced in Use Case #8
006 | 6.6.6 | Polls | Poll visitors online | In Progress | User goes to the webpage and scrolls down to participate in the poll | A website will need to embed a poll plugin | poll plugin | Website plugin |  |  |  |  | Referenced in Use Case #16
007 | 7.7.7 | Event Schedulilng | schedule and present events | In Progress | User goes to the webpage and scrolls down to see events | A website will need to embed a calendar with events or have an agenda interface listing events | calendar/agenda plugin | Website plugin |  |  |  |  | Referenced in Use Case #10
008 | 8.8.8 | Event Feedback | request feedback for events | In Progress | User goes to the webpage and clicks on recent events. Website gives option for feedback for those events | A website would need to have recent events listed and then have the poll pop up when the event title is clicked | survey moneky linked button | Survey Monkey |  |  |  |  | Referenced in Use Case #11
009 | 9.9.9 | Contact Us | Ability to contact employees | In Progress | User goes to webpage and clicks contact us | none. Just a webpage with mailto links | website | website |  |  |  |  | Referenced in Use Case #19
010 | 10.10.10 | Board of Directors Information Page | Ability to see/contact board of directors with relevant information | In Progress | User goes to webpage About -> Board of Directors | None. Just a webpage with links to director bios/ contact information | website | website |  |  |  |  | Referenced in Use Case #18
011 | 11.11.11 | Submit Photos | Ability for visitors to upload photos that would be moderated by KYHBPA employee | In Progress | User goes to photo gallery where a upload button is visible | A website will need to use an upload plugin that prevents files from being immediately accessible until they are screened | upload/review plugin | Website plugin |  |  |  |  | Referenced in Use Case #8
Note on A11: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B11: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C11: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on D11: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on E11: • Status: This column should be populated with the current status of the functional requirement.
Note on F11: • Architectural/Design Document: This column should be populated with a description of the architectural/design document linked to the functional requirement.
Note on G11: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on H11: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Note on I11: • Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Note on J11: • Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Note on K11: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on L11: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on M11: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.