## Requirement_Traceability_Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name | The Race to a New System
Project Type | Technical Organization
Project Start Date | 2017-02-15
Project End Date | 2017-05-02
Project Sponsor | Essential Systems
Primary Driver | Andrew Huff
Secondary Driver | Louis Ries
Division | Technology
Project Manager/Department | Krysta Albertson
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
001 | 1.1.1 | Payments can be made online. People need to donate online or order forms without having to travel to Louisville. | Process online payments | In Progress | User goes to the webpage and clicks donate or orders a document and enter their credit card informatiion into the page. | A website will just need to embed the PayPal payment button. | PayPal linked button | PayPal
002 | 2.2.2 | Newsletter and easier communication to members | Business Email | In Progress | Employee logs into new domain email to create and send emails or newsletters to members. | A newsletter signup and new domain will need to be created. | G- Suite | G- Suite
003 | 3.3.3 | Business continuity, storage, and disaster recovery | Microsoft Azure | In Progress | Database for the company and storage unit for important documents that are being stored in filing cabinets right now. | A Microsoft Azure account and setup will be required. | Microsoft Azure database and storage linked to website and domain email. | Microsoft Azure
Document Gallery
Form Submission
Note on A11: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B11: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C11: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on D11: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on E11: • Status: This column should be populated with the current status of the functional requirement.
Note on F11: • Architectural/Design Document: This column should be populated with a description of the architectural/design document linked to the functional requirement.
Note on G11: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on H11: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Note on I11: • Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Note on J11: • Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Note on K11: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on L11: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on M11: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.